## Requirements Matrix
CarismaSoft Requirements Matrix
Module | Feature ID | Feature Name | Priority | Effort (Days) | Status | Notes | Owner
Booking Engine | BE-001 | Real-time availability checking | Critical | 35 | Planned | Prevents double-booking | Dev Lead
Booking Engine | BE-002 | Online + internal booking | Critical | 28 | Planned | Multi-channel support | Dev Lead
Booking Engine | BE-003 | Staff fairness assignment | High | 18 | Planned | Load balancing algorithm | Dev Lead
Booking Engine | BE-004 | Manual override capability | High | 8 | Planned | Manager approval workflow | Dev Lead
Calendar System | CS-001 | Daily/Weekly/Monthly views | Critical | 25 | Planned | Multi-view support | Frontend
Calendar System | CS-002 | Per-location + global calendar | High | 20 | Planned | HQ visibility | Frontend
Calendar System | CS-003 | Drag & drop rescheduling | High | 15 | Planned | Real-time sync | Frontend
Multi-Location | ML-001 | Unified customer database | Critical | 30 | Planned | Across 13 locations | Backend
Multi-Location | ML-002 | Location-specific services | Critical | 22 | Planned | Pricing variations | Backend
Multi-Location | ML-003 | Cross-location staff conflicts | High | 20 | Planned | Prevent double-booking | Backend
Packages/Vouchers | PV-001 | Package creation & redemption | Critical | 28 | Planned | Partial redemption | Backend
Packages/Vouchers | PV-002 | Membership management | High | 18 | Planned | Recurring subscriptions | Backend
Packages/Vouchers | PV-003 | Gift voucher system | High | 12 | Planned | Digital tracking | Backend
Customer CRM | CRM-001 | Customer profile creation | Critical | 22 | Planned | Unified across locations | Backend
Customer CRM | CRM-002 | Booking history & preferences | High | 16 | Planned | Retention analytics | Backend
Payments | PAY-001 | Online payment processing | Critical | 25 | Planned | Stripe integration | Backend
Payments | PAY-002 | In-store POS integration | Critical | 30 | Planned | BOV POS sync | Backend
Payments | PAY-003 | Deposit & refund handling | High | 20 | Planned | Cancellation policy | Backend
Notifications | NOT-001 | WhatsApp reminders | High | 16 | Planned | Template-based | Backend
Notifications | NOT-002 | Email confirmations | High | 12 | Planned | Template-based | Backend
Roles & Permissions | RBAC-001 | Role definitions | Critical | 14 | Planned | 6 roles defined | Backend
Offline Mode | OFF-001 | Offline calendar access | Medium | 20 | Planned | View schedule offline | Frontend
API Layer | API-001 | REST API endpoints | Critical | 35 | Planned | Integration foundation | Backend
Migration | MIG-001 | Fresha data import | Critical | 22 | Planned | Customers, bookings, packages | Data Team

## Integrations
Integration Specifications
System | Type | Protocol | Sync Mode | Priority | Status | Notes
Zoho CRM | Customer Data | API | Real-time | Critical | Planned | Bidirectional sync
Zoho Books | Accounting | API | Daily Batch | High | Planned | Revenue posting
Zoho Inventory | Stock Management | API | Real-time | High | Planned | Product sync
Zoho Subscriptions | Billing | API | Real-time | High | Planned | Membership billing
Talexio | Payroll & Roster | API | Daily Batch | Critical | Planned | Staff sync, commissions
Stripe | Payments | API | Real-time | Critical | Planned | Card processing
BOV POS | In-store Payments | API/Webhook | Real-time | Critical | Planned | POS reconciliation
Klaviyo | Email Marketing | API | Event-based | Medium | Planned | Marketing automation
Zoho Analytics | Analytics | API | Daily Batch | Medium | Planned | Reporting dashboard

## Reports
Reporting Requirements
Report ID | Report Name | Category | Frequency | Primary Users | Status
R-001 | Daily Booking Summary | Operational | Daily | Manager, Receptionist | Planned
R-002 | Staff Utilization | Operational | Weekly | Location Manager | Planned
R-003 | Revenue by Location | Financial | Daily | Finance, HQ | Planned
R-004 | Revenue by Service | Financial | Weekly | Finance, Marketing | Planned
R-005 | Customer Acquisition Cost | Marketing | Monthly | CMO, Marketing | Planned
R-006 | No-show Rate | Operational | Weekly | Location Manager | Planned
R-007 | Package Usage Tracking | Operational | Monthly | Receptionist | Planned
R-008 | Staff Commission Report | Financial | Monthly | Payroll, Finance | Planned
R-009 | Customer Lifetime Value | Marketing | Monthly | CMO, Finance | Planned
R-010 | Cancellation Analysis | Operational | Weekly | Manager | Planned
R-011 | Inventory Forecast | Operational | Weekly | Inventory Manager | Planned
R-012 | Payment Reconciliation | Financial | Daily | Finance | Planned
R-013 | Multi-location Comparison | Operational | Monthly | HQ, CFO | Planned
R-014 | Customer Satisfaction | CRM | Monthly | Marketing, Manager | Planned
R-015 | Lead Source Attribution | Marketing | Monthly | CMO | Planned

## RBAC Matrix
Role-Based Access Control Matrix
Role / Permission | HQ Admin | Location Manager | Receptionist | Therapist | Doctor | Consultant
View All Bookings | ✓ | ✓ | - | - | ✓ | ✓
Create Booking | ✓ | ✓ | ✓ | - | ✓ | -
Edit Booking | ✓ | ✓ | ✓ | - | ✓ | -
Delete Booking | ✓ | - | - | - | - | -
Manage Staff | ✓ | ✓ | - | - | - | ✓
View Financials | ✓ | ✓ | - | - | - | ✓
Export Reports | ✓ | ✓ | - | - | - | -
Manage Packages | ✓ | ✓ | ✓ | - | - | -

## Timeline
Development Timeline & Milestones
Phase | Milestone | Start Week | Duration (Weeks) | Dev Days | Dependencies
Phase 1 (MVP) | M1: Planning & Architecture | 1 | 2 | 50 | None
Phase 1 (MVP) | M2: Booking Engine | 3 | 6 | 80 | M1
Phase 1 (MVP) | M3: Calendar & Scheduling | 9 | 5 | 65 | M2
Phase 1 (MVP) | M4: Multi-Location Logic | 14 | 5 | 60 | M2, M3
Phase 1 (MVP) | M5: Packages & CRM | 19 | 5 | 70 | M2, M4
Phase 1 (MVP) | M6: Payments & Notifications | 24 | 4 | 50 | M5
Phase 1 (MVP) | M7: Migration & Launch | 28 | 2 | 40 | M6

## Blind Spots
Blind Spots & Risks Identified
ID | Blind Spot | Category | Severity | Recommendation
1 | No-show policy undefined | Operational | Critical | Define refund/billing rules pre-kickoff
2 | Late cancellation handling | Operational | Critical | Specify deposit forfeiture logic
3 | EOD reconciliation workflow | Operational | High | Document therapist confirmation process
4 | Walk-in booking logic | Operational | High | Define payment, package usage, priority
5 | Recurring appointments | Operational | High | Specify series management & cancellation
6 | Race condition handling | Technical | Critical | Document concurrent booking logic
7 | Offline sync conflicts | Technical | High | Define conflict resolution algorithm
8 | Integration failure cascade | Technical | High | Specify fallback behaviors per system
9 | Payment reconciliation | Technical | High | Define Stripe vs BOV POS split logic
10 | Timezone handling | Technical | Medium | UTC standardization for multi-location

## Optimizations
Optimization & Innovation Ideas
ID | Idea | Category | ROI Impact | Complexity | Priority
1 | Dynamic pricing by demand | Revenue | High (+8-12%) | High | Phase 2
2 | No-show prediction AI | Efficiency | Medium (+3-5%) | Medium | Phase 2
3 | Upsell recommendations | Revenue | Medium (+5-8%) | Medium | Phase 2
4 | Customer lifetime value tracking | Analytics | Medium | Low | Phase 2
5 | Loyalty program integration | Revenue | Medium (+4-6%) | Medium | Phase 2
6 | AI booking assistant | UX | Medium | High | Phase 2
7 | Inventory forecasting | Efficiency | Medium | Medium | Phase 2
8 | Staff utilization optimization | Efficiency | High | Medium | Phase 2
9 | Marketing automation workflows | Marketing | Medium | Low | Phase 2

## Cost Breakdown
Development Cost & Timeline Analysis
COST SUMMARY
Category | Calculation | Cost (EUR)
Development (411 dev-days @ €475/day)
Infrastructure Setup (30%)
QA & Testing (25%)
Documentation & Training (10%)
Project Management (15%)
TOTAL YEAR 1 COST
Year 2+ Maintenance Cost
Hosting & Infrastructure | €12,000
Support & Maintenance (1 FTE) | €35,000
TOTAL ANNUAL

## Risks
Risk & Issue Matrix
ID | Risk/Issue | Category | Severity | Probability | Mitigation | Owner
1 | Fresha data export issues | Migration | Critical | High | Validate export format pre-cutover | Data Lead
2 | Talexio API integration delays | Integration | High | Medium | Parallel development with fallback | Backend Lead
3 | BOV POS payment sync failures | Integration | Critical | Medium | Real-time monitoring & alerts | Backend Lead
4 | Race condition in concurrent bookings | Technical | Critical | Medium | Database transactions + locking | Database Lead
5 | Multi-location staff conflicts | Operational | High | Low | Rigorous testing of scheduling logic | QA Lead
6 | Offline sync conflicts | Technical | High | Low | Conflict resolution algorithm design | Backend Lead